# Pack 7 — Deployment & Rollout Strategy

## Terra EOS v1 — 4.2 km Ecological Pilot

# 1) Phase 1 Objective (Clarity Above All)

This pilot is NOT about:

- Thousands of users

- Viral growth

- Perfect data

It is about proving:

- Grid-first ecological coordination works

- Corridor activation mechanics function

- Landholders understand and trust the scoring

- At least one cluster reaches ACTIVE

That’s success.

# 2) Pilot Rollout Sequence (Deliberate, Not Open Launch)

## Step 1 — Anchor Landholders (Strategic Selection)

Do NOT open publicly first.

Identify:

- 3–5 properties that:

  - Sit in high-leverage grids (High Uplift or Strategic Protection)

  - Are edge-adjacent

  - Have genuine restoration interest

These become:

Founding Stewards

They test:

- Claim flow

- Mission flow

- Evidence submission

- Cluster activation logic

Quietly.

## Step 2 — Corridor-First Recruitment

Instead of:
“Join Terra”

Say:

“We’re activating the Brookfield Riparian Corridor.”

Approach neighbours of founding properties.

Show them:

- Grid heatmap

- Corridor progress bar

- “This corridor activates when 3 of you participate.”

People respond to shared effort, not abstract scoring.

## Step 3 — First Cluster Activation (Critical Milestone)

Your first public milestone is:

Cluster Activated

Not:

- 100 users

- 500 missions

Once:

- ≥3 contiguous grids reach VERIFIED_UPLIFT

- Cluster state flips to ACTIVE

You announce it.

That’s proof of operating system function.

# 3) Field Playbook (How You Recruit a Corridor)

When approaching landholders:

Do not lead with:

- “App”

- “Platform”

- “Scoring”

Lead with:

“This stretch of land forms a critical corridor between X and Y.
If three of you coordinate, the system upgrades it to a Strategic Node.”

Then show:

- Their grid

- The neighbour grids

- The simple mission

Make it tangible.

# 4) Trust & Messaging Framework

This matters enormously.

You must clearly communicate:

- We do not regulate.

- We do not report to compliance authorities.

- Property boundaries are private.

- Grid performance is landscape-level.

Language matters.

The message:

“Terra helps neighbours coordinate ecological improvement —
it does not control land.”

# 5) Partner Strategy (Quiet Leverage)

For Phase 1, selectively involve:

- Local Landcare groups

- Environmental officers (informally)

- Academic observer (optional credibility layer)

Not to scale yet — but to:

- Observe

- Validate logic

- Provide language confidence

Keep governance clean and versioned.

# 6) Internal Rollout Timeline (12 Weeks)

Week 1–2
Kernel + scoring deployed on staging

Week 3–4
Grid visible in app (internal testing)

Week 5–6
Mission engine working (closed beta)

Week 7
3–5 founding landholders onboarded

Week 8–9
First corridor recruitment

Week 10
First missions verified

Week 11–12
First cluster activation attempt

# 7) Success Criteria (Pilot Completion Definition)

Pilot is successful if:

- ≥10 claimed properties

- ≥1 corridor cluster activated

- ≥20 missions started

- ≥10 verified uplift events

- ≥1 grid tier transition

- No major trust failures

That’s it.

Not 1,000 users.

# 8) Risk Management (Founder Safety Layer)

Major risks:

- Landholder suspicion

- Perceived regulatory threat

- Score misunderstanding

- Overclaiming ecological improvement

Mitigation:

- Always show “Explain My Score”

- Always show Confidence

- Always log model version

- Never inflate delta

Conservatism builds durability.

# 9) What You Should NOT Do in Phase 1

- Public marketing campaign

- Grant dependency

- Complex token or credit model

- Hardware integration

- Large corporate alignment

First prove the OS works at 4.2 km.

Then expand.

# 10) Strategic Positioning Statement (For Conversations)

Terra is:

A landscape-first ecological operating system that coordinates restoration across neighbouring landholders using a 1 km performance grid and transparent biodiversity scoring.

Clear. Strong. Non-threatening.