Phase 1 Corridor‑First Deployment Structure (50 Sensors)

Centrepoint (Gondwana pin): -27.490422615161563, 152.91568918292165

Footprint: 4.2 km radius circular pilot boundary; planning grid is 1 km × 1 km tiles indexed from the centre tile (0,0).

Seed nodes locked for Phase 1:

• Gondwana (PUC-17057): -27.490423, 152.915689  |  offsets ≈ (+0.00 km E, +0.00 km N)  |  tile T_0_0

• Andrew.grace.1981: -27.468685, 152.904706  |  offsets ≈ (-1.08 km E, +2.42 km N)  |  tile T_W1_N2

Corridor‑first deployment bands (allocation totals)

| Band | Intent | Sensors |
| --- | --- | --- |
| Band 1 – Gold Creek spine | Primary tributary corridor backbone (movement + riparian response). | 18 |
| Band 2 – Feeder micro-catchments | Headwater/feeder corridors including Gondwana watercourse; links toward Gold Creek. | 10 |
| Band 3 – Riparian buffer halo | Edge/transition zones adjacent to corridors; uplift measurement belt. | 8 |
| Band 4 – Ridge & upland connectors | Ridge/stepping‑stone connectors between drainage lines (lateral connectivity). | 8 |
| Band 5 – Control & interior mosaic | Controls + mixed‑use interior to keep inference defensible. | 6 |

Wave sequence (Terra → Founding 50)

Stage 1 (2–4 weeks): Terra Free to all parcels in footprint; show river/tributary context + registered‑properties overlay; no Founding 50 scarcity.

Stage 2: Launch Founding 50 invites only to Wave 1 tiles (Band 1).

Stage 3: Expand to Wave 2 (Bands 2–3), then Wave 3 (Bands 4–5) as corridor density builds.

Acoustic overlap planning (parameterised)

Use this as a tunable planning parameter (R) rather than a fixed assumption:

• R = effective detection radius (m) for target taxa + habitat + mic placement.

• Along corridors: target overlap of ~30–50% (spacing ≈ 1.0–1.4 × R).

• In interior/control: target overlap of ~0–20% (spacing ≈ 1.6–2.5 × R).

Calibrate R after first 2–3 deployments using empirical detection density and false‑positive rates.

30 vs 50 vs 70 sensor scenarios (rule‑of‑thumb)

• 30 sensors: corridor sampling only; weaker interior inference; best for proof‑of‑value.

• 50 sensors (selected): corridor + feeder + connectors + controls; balanced defensibility and practicality.

• 70 sensors: higher corridor granularity + replicated controls; stronger statistical power for uplift attribution.

Tile allocation file

A machine‑readable tile plan (centroids, band, wave, sensors per tile, seed nodes) is provided as CSV.